## Backlog
Issue ID | Type | Summary | Parent ID | Priority | Story points | Sprint | Owner | Story | Description
1 | Epic | E1 Data Pipeline |  | Medium |  | anti-spoofing |  |  | Datasets, manifest, EDA, subject-disjoint split, preprocessing.
2 | Epic | E2 Model Development |  | Medium |  | anti-spoofing |  |  | Baselines, fine-tuning, evaluation, threshold selection, ONNX/INT8 export.
3 | Epic | E3 Edge Device (Raspberry Pi) |  | Medium |  | anti-spoofing |  |  | Camera capture, on-device preprocessing, inference, decision engine, benchmarks.
4 | Epic | E4 Login Integration |  | Medium |  | anti-spoofing |  |  | Web login UI, backend auth API, security, logging, end-to-end demo.
5 | Epic | E5 MLOps & DevOps |  | Medium |  | anti-spoofing |  |  | CI/CD, versioning, monitoring, drift detection, retraining.
6 | Epic | E6 Project Management & Reporting |  | Medium |  | anti-spoofing |  |  | Group tasks, reports, demo video, meeting minutes.
7 | Feature | Group Task 1: system blueprint & project planning report | 6 | Highest | 5 | S0 | M1 |  | Group agreement, sprint plan, system blueprint, MLOps/DevOps design, Jira board, GitHub repository and documentation page.
8 | Task | Set up Jira board and GitHub repository | 6 | Medium |  | S0 | M1 |  | Create the Scrum board, sprints S0-S4 and the group GitHub repository structure.
9 | Feature | Final report, demo video and retrospective | 6 | High | 5 | S4 | M1 |  | Final evaluation report, end-to-end demo video and project retrospective.
11 | Feature | US1: Detect presentation attacks at login (print, screen, replay) | 4 | Highest | 8 | S2 | M1 | US1 | As a user logging in, I want the system to confirm that a live person is in front of the camera so that nobody can enter my account with my printed photo, a photo on a screen or a replayed video. ¦ Acceptance criteria: Print, screen and replay attacks are rejected in the demo; APCER, BPCER and ACER are reported per attack type on the held-out test set. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
12 | Feature | US2: Clear camera guidance and status messages | 4 | High | 5 | S3 | M1 | US2 | As a user, I want clear camera guidance and status messages so that I know how to pass the check and what to do when it fails. ¦ Acceptance criteria: Distinct messages for success, spoof suspected, low quality (dark, blurred, no face, several faces), timeout and technical failure; a retry button. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
13 | Feature | US3: Versioned subject-disjoint dataset split with frozen test set | 1 | Highest | 5 | S1 | M1 | US3 | As a data engineer, I want a versioned, subject-disjoint dataset split with a frozen test set so that model comparisons are fair and experiments are reproducible. ¦ Acceptance criteria: Manifest under DVC; automated check finds no subject overlap; test-set hash recorded before tuning. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
14 | Feature | US4: Compare and select the PAD model on validation data | 2 | Highest | 8 | S2 | M1 | US4 | As an ML engineer, I want to compare candidate models on validation data so that we select the model with the lowest attack acceptance inside our latency budget. ¦ Acceptance criteria: At least three models logged in MLflow; threshold chosen on validation; comparison table with APCER/BPCER/ACER and Pi latency. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
15 | Feature | US5: Run the anti-spoofing check on the Raspberry Pi | 3 | Highest | 8 | S1 | M1 | US5 | As a device operator, I want the anti-spoofing check to run on the Raspberry Pi so that face images never leave the device and the check stays fast. ¦ Acceptance criteria: INT8 ONNX model runs on Pi 5; inference p95 <= 50 ms per frame and <= 2 s per attempt; no images stored; result signed. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
16 | Feature | US6: Rate limiting, privacy-safe logging and fail-closed behaviour | 4 | High | 5 | S3 | M1 | US6 | As a security administrator, I want attempts to be rate-limited, logged without face images, and to fail closed so that attackers cannot brute-force or bypass the check and incidents can be audited. ¦ Acceptance criteria: Retry limit and lockout work; logs hold decision, score, model version, error code and timestamp only; a technical failure never results in a login. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
17 | Feature | US7: Monitoring and drift alerts that trigger retraining | 5 | Medium | 5 | S4 | M1 | US7 | As an ML engineer, I want monitoring and drift alerts that trigger retraining so that the model stays reliable when lighting, cameras or attack types change. ¦ Acceptance criteria: Weekly drift report (PSI) and audit APCER/BPCER tracked; retraining rules documented and dry-run once. ¦ Story owner: Dinh Phu Nguyen (M1). Backup: the other member.
101 | Subtask | T1: Download CelebA-Spoof; request Replay-Attack access via tutor; record licences | 13 | Highest |  | S1 | M2 | US3 | Owner: Phuc Lam Nguyen (M2). Backup owner: Dinh Phu Nguyen (M1). Planned sprint: S1. Estimate: 4 h.
102 | Subtask | T2: Build dataset manifest (path, label, subject, attack type, lighting, hash) and track with DVC | 13 | Highest |  | S1 | M1 | US3 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S1. Estimate: 6 h.
103 | Subtask | T3: EDA: class balance, attack types, lighting, images per subject | 13 | High |  | S1 | M2 | US3 | Owner: Phuc Lam Nguyen (M2). Backup owner: Dinh Phu Nguyen (M1). Planned sprint: S1. Estimate: 5 h.
104 | Subtask | T4: Subject-disjoint 80/10/10 split, leakage and near-duplicate checks, freeze test set | 13 | Highest |  | S1 | M1 | US3 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S1. Estimate: 5 h.
105 | Subtask | T5: Shared preprocessing module (YuNet detection, crop, resize, quality checks) + unit tests | 15 | Highest |  | S1 | M1 | US5 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S1. Estimate: 8 h.
106 | Subtask | T6: Set up Pi 5 (OS, Camera Module 3, picamera2); capture module with camera/video/mock sources | 15 | Highest |  | S1 | M1 | US5 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S1. Estimate: 6 h.
107 | Subtask | T7: Baselines: LBP+SVM and pre-trained MiniFASNet on validation | 14 | High |  | S2 | M1 | US4 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2. Estimate: 6 h.
108 | Subtask | T8: Fine-tune MiniFASNet and MobileNetV3-Small with augmentation; MLflow tracking | 14 | Highest |  | S2 | M1 | US4 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2. Estimate: 12 h.
109 | Subtask | T9: Evaluation script: APCER, BPCER, ACER, ROC-AUC, confusion matrix per attack type | 11 | Highest |  | S2 | M1 | US1 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2. Estimate: 6 h.
110 | Subtask | T10: Threshold selection on validation and model comparison table | 14 | High |  | S2 | M1 | US4 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2. Estimate: 4 h.
111 | Subtask | T11: ONNX export, INT8 quantisation, FP32 vs INT8 parity check | 15 | High |  | S2 | M1 | US5 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2. Estimate: 5 h.
112 | Subtask | T12: Pi latency and resource benchmark (median/p95, temperature, throttling) | 15 | High |  | S2 | M1 | US5 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S2-S3. Estimate: 5 h.
113 | Subtask | T13: Edge service: frame aggregation, decision engine, signed result (FastAPI + systemd) | 15 | Highest |  | S3 | M1 | US5 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 10 h.
114 | Subtask | T14: Backend auth API: password check, nonce issue, signature verification | 16 | Highest |  | S3 | M1 | US6 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 8 h.
115 | Subtask | T15: Web login UI with guidance and all status states | 12 | High |  | S3 | M1 | US2 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 10 h.
116 | Subtask | T16: Error states: camera unavailable, consent declined, timeout | 12 | High |  | S3 | M1 | US2 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 4 h.
117 | Subtask | T17: Rate limit, retry limit and lockout; structured logging without images | 16 | High |  | S3 | M1 | US6 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 5 h.
118 | Subtask | T18: Automated tests: pass, spoof, low quality, camera denied, timeout, repeated failures | 16 | Highest |  | S3 | M1 | US6 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3-S4. Estimate: 8 h.
119 | Subtask | T19: End-to-end integration and demo script (genuine user + print/screen/replay attacks) | 11 | Highest |  | S3 | M1 | US1 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 6 h.
120 | Subtask | T20: GitHub Actions CI: lint, pytest, data checks | 17 | Medium |  | S3 | M1 | US7 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S3. Estimate: 4 h.
121 | Subtask | T21: One-time test-set evaluation and consented Pi-camera sanity test | 11 | High |  | S4 | M1 | US1 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S4. Estimate: 6 h.
122 | Subtask | T22: Monitoring dashboard and weekly drift report (PSI) | 17 | Medium |  | S4 | M1 | US7 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S4. Estimate: 6 h.
123 | Subtask | T23: Retraining trigger rules, release and rollback procedure – document and dry-run | 17 | Medium |  | S4 | M1 | US7 | Owner: Dinh Phu Nguyen (M1). Backup owner: Phuc Lam Nguyen (M2). Planned sprint: S4. Estimate: 4 h.
200 | Subtask | Import backlog (epics, user stories, tasks) and create sprints S0-S4 | 8 |  |  | S0 | M1 |  | Planning task for sprint S0.
201 | Subtask | Group agreement, roles and sprint plan | 7 |  |  | S0 | M1 |  | Planning task for sprint S0.
202 | Subtask | System blueprint diagram | 7 |  |  | S0 | M1 |  | Planning task for sprint S0.
203 | Subtask | MLOps & DevOps design | 7 |  |  | S0 | M1 |  | Planning task for sprint S0.
204 | Subtask | User stories, backlog and task breakdown | 7 |  |  | S0 | M1 |  | Planning task for sprint S0.
205 | Subtask | Contribution statement and GenAI declaration | 7 |  |  | S0 | M1 |  | Planning task for sprint S0.
206 | Subtask | Dataset research notes (CelebA-Spoof, Replay-Attack) | 7 |  |  | S0 | M2 |  | Planning task for sprint S0.