COS40007 – Artificial Intelligence Engineering

Applied Project Task 1 (Group Task 1)

System Blueprint & Project Planning

Project: Anti-Spoofing for Secure Login – Edge Liveness Detection on Raspberry Pi 5

| Unit | COS40007 Artificial Intelligence Engineering |
| --- | --- |
| Task | Group Task 1 – System Blueprint & Project Planning (Studio Activity 5, Week 4) |
| Group No. | 3 |
| Group members | Dinh Phu Nguyen – Student ID: 105027282 Phuc Lam Nguyen – Student ID: 105006540 |
| Submission date | 25/10/2026 |
| GitHub repository | https://github.com/phu1009/COS40007---AI-Engineering- |

Acknowledgement of Country

We respectfully acknowledge the Wurundjeri People of the Kulin Nation, the Traditional Owners of the land on which Swinburne University of Technology's Australian campuses stand, and we pay our respects to their Elders past, present and emerging. We also acknowledge Aboriginal and Torres Strait Islander peoples as the Traditional Custodians of lands across Australia, and recognise their continuing connection to land, waters, culture and community.

- Group Agreement and Project Plan

- Studio Session No.: 5 (Week 4 Studio Activities – Group Task 1)

- Group No. (given by tutor only): 3

- Name and Students' Numbers of Group Members: Dinh Phu Nguyen (105027282); Phuc Lam Nguyen (105006540)

Group style and roles

Who does what, and how will you work together? Who will be responsible for the submitted deliverables? Who will ask questions on behalf of their group? Who is the Scrum Master for each Sprint or all sprints?

We are a two-member team. M1 leads the project and holds most technical roles; M2 supports with research and data preparation. We follow a light-weight Scrum process: one 1-week planning sprint and four 2-week delivery sprints, a sprint backlog in Jira, and a short review and retrospective at the end of every sprint. Every deliverable has one owner and one reviewer, so nothing is submitted without a second check, and every Jira task names a backup owner (the other member) in case of illness or non-delivery.

| Member | Roles | Main responsibilities | Owns these deliverables |
| --- | --- | --- | --- |
| M1 – Dinh Phu Nguyen | Scrum Master (all sprints) Group contact with tutor ML Engineer Edge / embedded engineer (Raspberry Pi) MLOps & DevOps lead Data, web/backend, QA & documentation | • Runs sprint planning, review and retrospective; keeps the sprint on schedule • Asks questions on behalf of the group and uploads all submissions to Canvas • Model training, comparison, threshold selection, ONNX / INT8 export • Raspberry Pi pipeline: camera capture, on-device preprocessing, inference, decision engine • GitHub repository rules, CI/CD workflows, model versioning • Data pipeline, web login UI, backend API, automated tests and documentation | All Task 1 sections Data pipeline & model package Pi edge service Web login prototype Reports and final submission |
| M2 – Phuc Lam Nguyen | Research assistant Data support | • Background research on candidate datasets and related work • Small data-preparation tasks (e.g. helping collect the consented Pi-camera test set) | Dataset research notes |
| Both | Reviewers of each other's work | • Weekly meeting, peer review of every pull request and report section, demo rehearsal, final report | Group report and demo video |

Decision rights. The role owner makes technical decisions inside their role and records them as a design decision (Section 4.4). Scope changes, and anything that affects marks or deadlines, are decided together in the weekly meeting. The tutor acts as the project stakeholder; M1 acts as product-owner proxy and orders the backlog, which M2 confirms at sprint planning.

Timeline (Follow Sprint here)

By when do you need to make decisions? When do tasks need to be completed by to ensure you submit on time? (Aim to submit BEFORE the deadline to allow for unforeseen circumstances).

Week numbers follow the teaching calendar on Canvas; the exact dates are set as sprint dates in Jira. Our internal deadline is 48 hours before every official deadline, each sprint keeps about 20% spare capacity for unplanned work, and Week 12 contains no new features.

| Sprint | Weeks | Sprint goal | Deliverables (definition of done) | Lead | Decision point / internal deadline |
| --- | --- | --- | --- | --- | --- |
| S0 | Wk 4 | Plan the project and set up tools | Group agreement, sprint plan, system blueprint, MLOps/DevOps design, Jira board, GitHub repository, documentation page → Group Task 1 PDF | M1 | Scope fixed (passive liveness first) and datasets chosen by end of Wk 4 |
| S1 | Wk 5–6 | Data pipeline ready; Pi capturing frames | CelebA-Spoof downloaded; Replay-Attack EULA requested through tutor; manifest + DVC; EDA; subject-disjoint split with frozen test set; shared preprocessing module; Pi 5 set up with camera capture and face-detection benchmark | M1 (M2: dataset research) | Test split frozen by end of Wk 5; Pi capture working by end of Wk 6 |
| S2 | Wk 7–8 | Train, compare and select the model | LBP+SVM and pre-trained MiniFASNet baselines; fine-tuned MiniFASNet and MobileNetV3-Small; MLflow runs; evaluation script; threshold on validation; ONNX + INT8 export; Pi latency benchmark | M1 | Model selected by end of Wk 8 (APCER/BPCER on validation + Pi p95 latency) |
| S3 | Wk 9–10 | Integrate the end-to-end login flow | Pi edge service with decision engine and signed results; backend auth API; web login UI with all guidance states; logging without images; GitHub Actions CI (lint + tests) | M1 | Feature freeze at end of Wk 10 |
| S4 | Wk 11–12 | Evaluate, monitor, document and demo | One-time test-set evaluation per attack type; Pi-camera sanity test (consented); monitoring and drift report; full automated test suite; final report and demo video; retrospective | M1 (M2: Pi-camera data collection) | Final report complete 3 days before deadline; demo rehearsal in Wk 12 |

Simple timeline (Gantt view). Coloured cells show when each workstream is active and who leads it; colours match the sprint badges in the system blueprint (Figure 1).

| Workstream | Wk 4 (S0) | Wk 5 (S1) | Wk 6 (S1) | Wk 7 (S2) | Wk 8 (S2) | Wk 9 (S3) | Wk 10 (S3) | Wk 11 (S4) | Wk 12 (S4) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning, Jira & GitHub setup | M1 |  |  |  |  |  |  |  |  |
| Dataset research | M2 | M2 |  |  |  |  |  |  |  |
| Data pipeline, EDA & split |  | M1 | M1 | M1 |  |  |  |  |  |
| Raspberry Pi edge pipeline |  | M1 | M1 |  | M1 | M1 | M1 |  |  |
| Model training & selection |  |  |  | M1 | M1 |  |  |  |  |
| Web UI & backend integration |  |  |  |  |  | M1 | M1 |  |  |
| Testing & evaluation |  |  |  |  | M1 |  | M1 | M1 | M1 |
| MLOps: CI/CD, monitoring, drift | M1 |  |  |  |  |  | M1 | M1 | M1 |
| Report, documentation & demo | M1 |  |  |  |  |  |  | M1 | M1 |

Scope control (MoSCoW). 
	Must: passive liveness running on the Pi, web login demo, APCER/BPCER/ACER and latency report, fail-safe states. 
	Should: optional blink challenge as a second step, drift dashboard. 
	Could: Camera Module 3 NoIR with infrared lighting, comparison with a Hailo AI HAT+. Won't (this semester): face recognition / identity matching, a native mobile app, 3D-mask attacks. Keeping the Must list small is what makes this plan realistic for a two-person team.

Communication Plan

Decide and document how your group will communicate and collaborate regularly throughout the project. This could include meeting via Zoom, communicating via a Teams group or Canvas, and using cloud services for shared documents, etc. How often and how will you communicate? What are your expectations of others responding to your communications?

| Channel | Frequency / timing | Purpose and rules |
| --- | --- | --- |
| Sprint meeting (Microsoft Teams or in person after the studio) | Weekly, Monday, 45 min | Progress, blockers, next tasks. Minutes are written in the documentation page within 24 h and actions are added to Jira. |
| Asynchronous stand-up (group chat on Teams/Messenger) | Mon, Wed, Fri by 21:00 | Three lines: done / next / blocked. Missing two stand-ups in a row starts the tension process below. |
| Sprint review + retrospective | Last day of each sprint, 30 min | Demo of finished work against the definition of done; one thing to keep, one to change. |
| Jira | Continuously | Single source of truth for tasks, owners, priorities and sprint progress. |
| GitHub | Continuously | Code, pull-request reviews and issues; branch names and commits carry the Jira key (e.g. SCRUM-23). |
| Google Drive / OneDrive + Notion (or Word) | Continuously | Report drafts, meeting minutes, design decisions and documentation. |
| Canvas / email to tutor | As needed | Official questions (asked by M1 on behalf of the group) and all submissions. |

Response expectations. Messages are answered within 24 hours on weekdays and 48 hours at weekends; within 6 hours when a deadline is less than 48 hours away. Pull requests are reviewed within 48 hours. A member who will be unavailable posts a notice in advance and hands over open tasks.

On-track behaviours

What behaviours will result in great group outcomes?

- Updating Jira when starting or finishing a task, and linking commits and pull requests to Jira keys so work is visible.

- Meeting the internal deadline (48 h early), or warning the team at least 48 h ahead when a task is at risk.

- Small, reviewed pull requests with tests; no direct pushes to the main branch.

- Asking for help within one day of being blocked instead of waiting until the deadline.

- Reporting results honestly, including poor ones, and recording contributions and GenAI use accurately.

- Respecting dataset licences and privacy: no dataset files, face images or credentials shared outside the team's approved storage.

Off-track behaviours

What behaviours would result in group outcomes that are not great?

- Missing meetings without notice, or not responding for more than 48 hours.

- Missing internal deadlines without warning, or submitting unreviewed, last-minute work.

- Working outside Jira and GitHub so that work cannot be seen, reviewed or verified.

- Copying code or text without attribution, or using GenAI without declaring it.

- Tuning the model on the test set or reporting only favourable metrics.

- Storing or sharing raw face images, credentials or dataset files outside approved storage.

Resolving tensions

How will we resolve tensions or off-track behaviour as a group?

We use a four-step escalation path so problems are dealt with early and fairly:

- 1. Talk early. Raise the issue privately and respectfully within 24 hours, focusing on the task rather than the person, and agree on a fix and a new date.

- 2. Record and re-plan. If it is not resolved, discuss it at the weekly meeting; the agreed actions, new owner and date are written in the minutes and in Jira.

- 3. Formal notice and reallocation. If a member misses two agreed commitments in one sprint or is unresponsive for 72 hours, the other member sends a written notice in the group chat. The affected tasks move to the backup owner and the change is logged in Jira, so contribution records stay accurate.

- 4. Escalate to the tutor. If the problem continues into the next sprint, we contact the tutor before the next submission with evidence (Jira history, GitHub commits, meeting minutes) and ask for mediation. Contribution statements always reflect the work actually done.

Technical disagreements are settled with evidence (validation metrics, latency measured on the Pi) and time-boxed to 30 minutes; if there is still no agreement, the role owner decides and records the reasoning as a design decision.

Team Expectations:

| 1. | Commitment and reliability: attend the weekly meeting, finish sprint tasks by the internal deadline (48 h before the official deadline) and keep Jira up to date. |
| --- | --- |
| 2. | Quality and review: every deliverable (code, model, report section) is reviewed by the other member before submission; code is merged only through a pull request with passing checks. |
| 3. | Integrity and privacy: contributions, results and GenAI use are reported honestly; dataset licences are respected and no raw face images, credentials or dataset files leave approved storage. |

- System Blueprint Diagram: A diagram showing system components, data flow, and ML model integration with an explanation relevant to your applied project.

Figure 1. System blueprint: components, data flow, ML model integration and the sprint in which each stage is built. Editable draw.io source: Group Project/docs/architecture/system_blueprint.drawio in the group GitHub repository.

2.1 How the system works

The system has three layers connected by a shared DevOps/MLOps backbone. The offline ML pipeline (stages 1–6) turns public presentation-attack datasets into a versioned, validated model package. The Raspberry Pi edge device (stages 7–11) runs the liveness check next to the camera, so face images never leave the device; it outputs a decision with a confidence score. The application and operations layer (stages 12–15) combines that decision with the password check in the web login flow and watches the system in production, closing the retraining loop.

Login sequence (numbered arrows in Figure 1). ① The user submits username and password in the web UI. ② The backend checks the password and sends a short-lived session ID and random nonce to the Pi. ③ The Pi captures frames, runs the model and returns a result signed with its device key and bound to that nonce. ④ The backend verifies the signature and freshness, applies rate limits and returns the final decision to the UI. ⑤ Every attempt is logged without images. ⑥ Monitoring can trigger retraining, which feeds back into stage 2.

| Stage (Figure 1) | What happens in our project | Why – design rationale and dataset (EDA) insight | Sprint |
| --- | --- | --- | --- |
| Data sources & ingestion (1–2) | CelebA-Spoof is the main dataset (625,537 images, 10,177 subjects; print, replay and paper-mask attacks; 4 lighting conditions). Replay-Attack (print and phone/tablet replay, 320×240 webcam) is used for cross-dataset testing; a small consented Pi-camera set for testing only. Scripts build a DVC-versioned manifest (path, label, subject, attack type, lighting, hash). | Licences forbid redistribution, so raw data never goes to GitHub; the manifest makes every split reproducible. Replay-Attack needs a staff EULA, so we request it through the tutor. | S0–S1 |
| Preprocessing (3) | YuNet face detection; crop the box enlarged 2.7×; resize to 80×80; normalise; quality filter (blur, brightness, face size); subject-disjoint 80/10/10 split; near-duplicate check; test set frozen before any tuning. | Each subject has many images, so a random split would leak identities into the test set. The same module is reused on the Pi to avoid training/serving skew. | S1 |
| Feature engineering (4) | The CNN learns features end-to-end; LBP texture histograms feed the classical baseline; augmentation varies lighting, blur, JPEG quality and colour. | CelebA-Spoof labels four lighting conditions (normal, strong, back-lit, dark), and the Pi camera differs from the dataset cameras, so augmentation targets these shifts. | S1–S2 |
| ML model (5–6) | Compare LBP+SVM, pre-trained MiniFASNet, fine-tuned MiniFASNet and MobileNetV3-Small (class-weighted loss). Threshold set on validation; APCER, BPCER, ACER, precision, recall, F1 and ROC-AUC per attack type. Export ONNX → INT8. | Live:spoof ≈ 1:3, so accuracy misleads; we pick the lowest APCER at BPCER ≤ 5% within the Pi latency budget (ISO/IEC 30107-3 metrics). Models under 5 MB run on the Pi CPU. | S2 (final test S4) |
| Edge inference & model output (7–11) | After the user taps Start, the Pi captures 10–15 frames, preprocesses them, runs ONNX Runtime and takes the median live score. Output: PASS, SPOOF SUSPECTED, RETRY (low quality) or TECHNICAL FAILURE, with score, threshold, model version and processing time. | Biometric images stay on the device; multi-frame aggregation reduces single-frame errors; technical errors fail closed (spec requirement). | S1, S2–S3 |
| UI & system integration (12–13) | Web login page with camera guidance and clear status messages; FastAPI backend that issues the nonce, verifies the Pi signature, enforces retry and rate limits and makes the final decision. | Login continues only when the password and the liveness check both pass; signing stops forged or replayed "pass" messages. | S3 |
| Monitoring & retraining (14–15) | Structured attempt logs (no images), dashboard, weekly red-team audit with known attacks, drift detection that triggers retraining. | Explained in Section 3. | S3–S4 |

- MLOps & DevOps Integration (High-Level Design): How MLOps (retraining, monitoring) and DevOps (CI/CD, version control) will fit into your project.

Our MLOps goal is a model that can be reproduced, deployed safely to the Raspberry Pi and kept reliable as lighting, cameras and attack methods change. One project constraint shapes the whole design: the specification forbids storing raw face images by default, so we cannot collect production images for retraining. New training data therefore comes only from public datasets and explicitly consented collection sessions, and production monitoring works on aggregate statistics.

3.1 Data & training strategy

- Split. CelebA-Spoof is split 80/10/10 into training, validation and test sets by subject, stratified by live/spoof and attack type. Replay-Attack keeps its official train/devel/test protocol (no client overlap) and is used as a cross-dataset test. The consented Pi-camera set is test-only.

- Frozen test set. The test set is frozen (hash stored in the manifest) before tuning. Model, threshold and hyper-parameters are chosen on validation data only; the test set is run once per release candidate, for reporting, never for selection.

- Leakage controls. Automated checks for subject overlap and near-duplicate frames (perceptual hash) run in CI; augmentation is applied to training data only.

- New data for retraining – yes, under control. New data comes from (a) new public dataset versions, (b) consented Pi-camera sessions recorded by the team (live and attack samples), and (c) red-team sessions with new attack instruments such as a new phone or OLED screen. It enters through the same ingestion pipeline as a new DVC version; new subjects go to training/validation, while a fixed Pi-domain test set is kept so results stay comparable.

3.2 Retraining strategy

| Trigger | Rule (our thresholds) | Action |
| --- | --- | --- |
| Time-based | Monthly retraining review (during the semester: at the end of each sprint). | Retrain if new data is ≥ 10% of the training set or a new attack type was collected; otherwise record "no change" in the model log. |
| Performance-based | Weekly red-team audit shows APCER > 10% or BPCER > 10%, or ACER worse than the released model by more than 3 percentage points. | Collect labelled examples of the failure cases, retrain, re-evaluate. |
| Drift-based | PSI > 0.2 on input-quality features or on the live-score distribution for two consecutive weeks (Section 3.3). | Investigate the cause; if the audit set confirms a drop, retrain with data covering the new conditions. |
| Event-based | New camera or hardware, a newly discovered attack instrument, or an ONNX Runtime / OS upgrade. | Re-run the evaluation and Pi benchmark; retrain if the gates in the next paragraph fail. |

Frequency and process. We expect about one retraining per month (at most one per sprint during the semester), plus ad-hoc runs when a trigger fires. Retraining follows a champion–challenger process: the new model must (1) match or beat the current model's APCER at BPCER ≤ 5% on validation and on the red-team audit set, (2) keep per-frame inference p95 ≤ 50 ms and a full attempt p95 ≤ 2 s on the Pi 5, and (3) pass all automated tests. It is then registered, released, run in shadow mode on the Pi (scores logged, decisions not used) for one audit session, and only then promoted. The previous version stays available for one-step rollback.

3.3 Monitoring & drift detection

| What we monitor | Metrics | Where / how | Alert when |
| --- | --- | --- | --- |
| Service health (Pi + backend) | Latency p50/p95 per stage, CPU temperature and throttling flags, memory, technical-failure rate | Pi telemetry → backend log store → dashboard | p95 attempt > 2 s or failure rate > 1% |
| Model behaviour (no labels) | Distribution of live scores, pass / spoof / retry rates, share of scores close to the threshold | Structured attempt logs | Pass rate changes by > 15% vs. the reference week |
| Input data quality | Brightness, blur (Laplacian variance), face size, head pose, number of faces | Computed on the Pi, sent as aggregates | PSI > 0.2 |
| Labelled performance | APCER, BPCER, ACER per attack type | Weekly red-team audit: known live and attack sessions | APCER or BPCER > 10% |

Data drift means the inputs change, for example new room lighting or a different camera. We compare each week's distributions of the input-quality features and live scores with a reference window (validation statistics and the first deployment week) using the Population Stability Index and, for continuous features, the Kolmogorov–Smirnov test.

Concept drift means the relationship between input and label changes, for example a new high-resolution OLED phone or better prints that the model now accepts as live. Input statistics can look normal while this happens, so we detect it through the labelled weekly red-team audit (rising APCER), a growing share of borderline scores, and reported false accepts or rejects. The response is to collect labelled samples of the new attack, retrain, and update the list of attacks documented as out of scope. All monitoring uses scores and aggregate statistics only; no face images are logged.

3.4 DevOps practices

Version control strategy. We will use GitHub. All code, configuration and documentation live in one group repository. The main branch is protected: changes arrive only through pull requests with one review and passing checks. Short-lived feature branches are named after Jira keys (e.g. feature/SCRUM-23-pi-capture) and commit messages start with the key, so Jira and GitHub stay linked. Releases are tagged vMAJOR.MINOR.PATCH. Datasets, face images and secrets are excluded by .gitignore; secrets live in GitHub Secrets.

CI/CD pipeline concept (GitHub Actions – to be implemented in a later task).

| Workflow | Trigger | Steps |
| --- | --- | --- |
| CI – ci.yml | Every pull request and push to main | Lint and format check (ruff); unit tests with pytest, using recorded videos instead of a real camera; manifest schema and leakage checks; smoke inference on 20 fixture images comparing FP32 and INT8 outputs. |
| Train & evaluate – train.yml | Manual dispatch or monthly schedule | Run training on a GPU runner (Colab or a self-hosted runner, because GitHub-hosted runners have no GPU); log to MLflow; apply the evaluation gate from Section 3.2; fail the workflow if the gate is not met. |
| Release / CD – release.yml | Git tag v* | Build the model package (ONNX INT8 + threshold config + model card + checksum) and publish a GitHub Release. The Pi pulls the release (updater service or self-hosted runner), verifies the checksum, runs an on-device smoke test and latency check, starts shadow mode, then promotes; it rolls back automatically if the smoke test fails. |

Code and model versioning.

| Artefact | Tool | Version identifier |
| --- | --- | --- |
| Source code, configs (threshold, preprocessing) | Git + GitHub | Commit SHA and release tag |
| Datasets, splits, manifests | DVC (remote: shared Google Drive) | DVC hash + dataset version, e.g. data-v1.2 |
| Experiments | MLflow tracking | Run ID with parameters, metrics, Git SHA and data version |
| Trained models | MLflow Model Registry + GitHub Releases | pad-model vMAJOR.MINOR.PATCH (major = new architecture, minor = retrain, patch = threshold/config change) |
| Runtime environment | Pinned requirements file + Pi setup notes | Locked package versions per release |

Every login attempt record stores the model version and config version, so any decision can be traced back to the exact code commit, dataset version and training run.

- Project Management Setup (Agile Tools): A Jira (or Trello or others) board with key user stories and a Confluence/Notion/Word page for project documentation.

4.1 Jira board

We use Jira Software (Scrum template) with project key SCRUM (Group 3 Jira space). The board has six epics – E1 Data Pipeline, E2 Model Development, E3 Edge Device (Raspberry Pi), E4 Login Integration, E5 MLOps & DevOps, E6 Project Management & Reporting – and five sprints (S0–S4) that match Section 1. User stories (Jira "Feature" work items) are estimated in story points; tasks carry an owner, a backup owner, a priority and hour estimates. Workflow: Idea → To Do → In Progress → Testing → Done (Testing is our review step). A task is Done when its acceptance criteria pass, the pull request is reviewed and merged, and any documentation is updated. Board link: https://group3-cos40007.atlassian.net/jira/software/projects/SCRUM/boards/1.

Figure 2. Jira backlog: sprints S0–S4 with the user stories (US1–US7), epics, owners, priorities and story-point estimates.

Figure 3. Jira board for the active sprint S0 (grouped by subtask): planning tasks moving through To Do, In Progress, Testing and Done.

4.2 User stories

| ID | User story | Acceptance criteria | Priority | SP | Sprint | Owner / epic |
| --- | --- | --- | --- | --- | --- | --- |
| US1 | As a user logging in, I want the system to confirm that a live person is in front of the camera so that nobody can enter my account with my printed photo, a photo on a screen or a replayed video. | Print, screen and replay attacks are rejected in the demo; APCER, BPCER and ACER are reported per attack type on the held-out test set. | Highest | 8 | S2–S3 | M1 / E4 |
| US2 | As a user, I want clear camera guidance and status messages so that I know how to pass the check and what to do when it fails. | Distinct messages for success, spoof suspected, low quality (dark, blurred, no face, several faces), timeout and technical failure; a retry button. | High | 5 | S3 | M1 / E4 |
| US3 | As a data engineer, I want a versioned, subject-disjoint dataset split with a frozen test set so that model comparisons are fair and experiments are reproducible. | Manifest under DVC; automated check finds no subject overlap; test-set hash recorded before tuning. | Highest | 5 | S1 | M1 / E1 |
| US4 | As an ML engineer, I want to compare candidate models on validation data so that we select the model with the lowest attack acceptance inside our latency budget. | At least three models logged in MLflow; threshold chosen on validation; comparison table with APCER/BPCER/ACER and Pi latency. | Highest | 8 | S2 | M1 / E2 |
| US5 | As a device operator, I want the anti-spoofing check to run on the Raspberry Pi so that face images never leave the device and the check stays fast. | INT8 ONNX model runs on Pi 5; inference p95 ≤ 50 ms per frame and ≤ 2 s per attempt; no images stored; result signed. | Highest | 8 | S1–S3 | M1 / E3 |
| US6 | As a security administrator, I want attempts to be rate-limited, logged without face images, and to fail closed so that attackers cannot brute-force or bypass the check and incidents can be audited. | Retry limit and lockout work; logs hold decision, score, model version, error code and timestamp only; a technical failure never results in a login. | High | 5 | S3 | M1 / E4 |
| US7 | As an ML engineer, I want monitoring and drift alerts that trigger retraining so that the model stays reliable when lighting, cameras or attack types change. | Weekly drift report (PSI) and audit APCER/BPCER tracked; retraining rules documented and dry-run once. | Medium | 5 | S4 | M1 / E5 |

4.3 Backlog and task breakdown

User stories are broken into tasks (imported into Jira as sub-tasks of each story, so Jira assigned SCRUM keys, e.g. T1 = SCRUM-18); each task has one owner and the other member is always the backup owner. M1 owns most tasks (≈ 134 h); M2 supports dataset research and data preparation (≈ 9 h). Priorities follow the MoSCoW scope in Section 1.

| ID | Task | Story | Owner | Priority | Sprint | Est. (h) |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Download CelebA-Spoof; request Replay-Attack access via tutor; record licences | US3 | M2 | Highest | S1 | 4 |
| T2 | Build dataset manifest (path, label, subject, attack type, lighting, hash) and track with DVC | US3 | M1 | Highest | S1 | 6 |
| T3 | EDA: class balance, attack types, lighting, images per subject | US3 | M2 | High | S1 | 5 |
| T4 | Subject-disjoint 80/10/10 split, leakage and near-duplicate checks, freeze test set | US3 | M1 | Highest | S1 | 5 |
| T5 | Shared preprocessing module (YuNet detection, crop, resize, quality checks) + unit tests | US5 | M1 | Highest | S1 | 8 |
| T6 | Set up Pi 5 (OS, Camera Module 3, picamera2); capture module with camera/video/mock sources | US5 | M1 | Highest | S1 | 6 |
| T7 | Baselines: LBP+SVM and pre-trained MiniFASNet on validation | US4 | M1 | High | S2 | 6 |
| T8 | Fine-tune MiniFASNet and MobileNetV3-Small with augmentation; MLflow tracking | US4 | M1 | Highest | S2 | 12 |
| T9 | Evaluation script: APCER, BPCER, ACER, ROC-AUC, confusion matrix per attack type | US1 | M1 | Highest | S2 | 6 |
| T10 | Threshold selection on validation and model comparison table | US4 | M1 | High | S2 | 4 |
| T11 | ONNX export, INT8 quantisation, FP32 vs INT8 parity check | US5 | M1 | High | S2 | 5 |
| T12 | Pi latency and resource benchmark (median/p95, temperature, throttling) | US5 | M1 | High | S2–S3 | 5 |
| T13 | Edge service: frame aggregation, decision engine, signed result (FastAPI + systemd) | US5 | M1 | Highest | S3 | 10 |
| T14 | Backend auth API: password check, nonce issue, signature verification | US6 | M1 | Highest | S3 | 8 |
| T15 | Web login UI with guidance and all status states | US2 | M1 | High | S3 | 10 |
| T16 | Error states: camera unavailable, consent declined, timeout | US2 | M1 | High | S3 | 4 |
| T17 | Rate limit, retry limit and lockout; structured logging without images | US6 | M1 | High | S3 | 5 |
| T18 | Automated tests: pass, spoof, low quality, camera denied, timeout, repeated failures | US6 | M1 | Highest | S3–S4 | 8 |
| T19 | End-to-end integration and demo script (genuine user + print/screen/replay attacks) | US1 | M1 | Highest | S3 | 6 |
| T20 | GitHub Actions CI: lint, pytest, data checks | US7 | M1 | Medium | S3 | 4 |
| T21 | One-time test-set evaluation and consented Pi-camera sanity test | US1 | M1 | High | S4 | 6 |
| T22 | Monitoring dashboard and weekly drift report (PSI) | US7 | M1 | Medium | S4 | 6 |
| T23 | Retraining trigger rules, release and rollback procedure – document and dry-run | US7 | M1 | Medium | S4 | 4 |

Project-management tasks (Task 1 report, final report, demo video, weekly minutes) sit under epic E6 and are shared by both members.

4.4 Project documentation (shared space)

Our shared documentation space is a Word page, Project_Documentation.docx, stored in Group Project/docs/ of the GitHub repository (https://github.com/phu1009/COS40007---AI-Engineering-). It contains the project description, the system overview (Figure 1 and Section 2.1), meeting minutes and the key design decisions below.

| ID | Key design decision | Reason |
| --- | --- | --- |
| DD1 | Run the liveness check on the Raspberry Pi (edge), not in the cloud | Face images stay on the device; latency and resource use are measured on the real target hardware. Trade-off: limited compute, so only lightweight models. |
| DD2 | Passive liveness first; blink challenge only as an optional second step | Passive detection covers print, screen and replay attacks with no user effort; a replayed video can contain blinks, so a blink check alone is weak. |
| DD3 | Lightweight CNN (MiniFASNet / MobileNetV3-Small) exported to ONNX INT8; LBP+SVM as baseline | Under 5 MB, runs on the Pi CPU without an accelerator; the baseline shows what deep learning adds. |
| DD4 | Subject-disjoint split, frozen test set, threshold chosen on validation | Prevents identity leakage and optimistic results, as required by the project specification. |
| DD5 | Select the model by APCER at BPCER ≤ 5% plus Pi p95 latency, not by accuracy | Classes are imbalanced (about 1:3) and accepting an attack costs more than asking a genuine user to retry. |
| DD6 | Pi results are signed and bound to a server nonce; technical errors fail closed | Stops forged or replayed "pass" messages; a failure can never bypass the check. |
| DD7 | No raw face images in logs; monitoring on aggregates; retraining only with consented data | Meets the privacy requirement of the specification and university ethics expectations. |
| DD8 | GitHub + DVC + MLflow for versioning; GitHub Actions for CI/CD | Free tools that link code, data, experiments and models for full reproducibility. |

- Contribution Statement

Contributions below describe the work each member actually did on Group Task 1 and can be checked against the GitHub history.

| Member | Contribution to Group Task 1 | Share (%) |
| --- | --- | --- |
| Dinh Phu Nguyen 105027282 | • Analysed the task brief, rubric, template and project specification • Designed the system architecture and drew the system blueprint (Figure 1) • Wrote the group agreement, sprint plan and timeline (Section 1) • Wrote the MLOps & DevOps design (Section 3) • Wrote the user stories and task breakdown; set up the Jira board and the GitHub repository • Prepared the project documentation, compiled and proofread the report, and submitted it | 90% |
| Phuc Lam Nguyen 105006540 | • Background research on candidate datasets (CelebA-Spoof, Replay-Attack) • Small data-preparation support | 10% |

- Generative AI Declaration

We used generative AI in this task. 
Tool: Claude (Anthropic), 
 Purpose: (1) analysing the task brief, rubric and template; (2) helping draft parts of the report and the user stories
 Proof: screenshots in Appendix A.

- Links

- Group GitHub repository: https://github.com/phu1009/COS40007---AI-Engineering- – Task 1 files are in Group Project/docs/ (report in docs/task1/, blueprint source in docs/architecture/, Jira import in docs/jira/).

- Jira board: https://group3-cos40007.atlassian.net/jira/software/projects/SCRUM/boards/1

- Project documentation: Word file Group Project/docs/Project_Documentation.docx in the GitHub repository

References

Chingovska, I, Anjos, A & Marcel, S 2012, 'On the effectiveness of local binary patterns in face anti-spoofing', Proceedings of the International Conference of the Biometrics Special Interest Group (BIOSIG), IEEE.

GitHub 2026, GitHub Actions documentation, GitHub Docs, viewed 25 October 2026, <https://docs.github.com/actions>.

ISO/IEC 30107-3:2023, Information technology – Biometric presentation attack detection – Part 3: Testing and reporting, International Organization for Standardization, Geneva.

Martinez-Diaz, Y et al. 2023, 'Exploring the effectiveness of lightweight architectures for face anti-spoofing', Proceedings of the IEEE/CVF Conference on Computer Vision and Pattern Recognition Workshops (CVPRW), IEEE.

Raspberry Pi Ltd 2026, Camera software and AI Camera documentation, viewed 25 October 2026, <https://www.raspberrypi.com/documentation/>.

Zhang, Y, Yin, Z, Li, Y, Yin, G, Yan, J, Shao, J & Liu, Z 2020, 'CelebA-Spoof: large-scale face anti-spoofing dataset with rich annotations', European Conference on Computer Vision (ECCV), Springer, pp. 70–85.

Appendix A – GenAI evidence:

	(1) analysing the task brief, rubric and template:						(2) helping draft parts of the report and the user stories: